DataForge

Project Roadmap

12-Month Prototype Delivery Plan

Team: Abdalla · Beyza · Omer

Period: 11 May 2026 — 9 April 2027

# 1. Project Overview

DataForge is a 12-month prototype project adapted from the Dataseed Yazılım Elektronik R&D proposal (36-month industrial version). Our team will build a working real-time data processing prototype that demonstrates CERN ALICE O² principles applied to defense and industrial sensor data.

The final deliverable is a presentable working prototype that the Dataseed team can take forward into the full industrial build. The prototype targets TRL 4-5 (validated component in laboratory environment), not the TRL 5-7 operational deployment described in the full proposal.

## Core Pipeline

ALICE Data + Synthetic Sensor Data → Data Adaptation → Kafka Streaming → Spark Processing → Data Fusion → AI/ML Anomaly Detection → Explainable AI → Dashboard + API

# 2. Team Structure

| Member | Role | Key Areas |
| --- | --- | --- |
| Abdalla | Project Lead | Architecture, AI/ML, XAI logic, documentation, team coordination |
| Beyza | Full-Stack Developer | Dashboard (ReactJS), FastAPI backend, TimescaleDB, UI/UX |
| Omer | Data Engineer | Kafka/Spark streaming, Docker, data simulation, performance testing |

## Supervision & Advisory

- Supervisor: Emrah Uysal — Dataseed Yazılım Elektronik (weekly written update every Friday)

- Scientific Advisor: Prof. Dr. Ayben Karasu Uysal — Yıldız Teknik Üniversitesi (consulted through Emrah on ALICE data and scientific methodology)

# 3. Scope Reconciliation

The official Dataseed proposal targets a 36-month, industrial-grade build with TRL 5-7 outcomes. Our prototype is a 12-month subset with the same architecture but scaled-down performance expectations, designed to demonstrate correctness of the pipeline and AI logic. The performance numbers scale with hardware; the prototype runs entirely on team laptops via Docker Compose.

## Performance Targets — Industrial vs Prototype

| Metric | Industrial Target | Prototype Bar | Notes |
| --- | --- | --- | --- |
| Throughput | ≥200K events/sec | ≥10K events/sec | Single-broker Kafka on Docker |
| Latency (p95) | ≤50 ms | ≤500 ms | Docker network overhead |
| Data Loss | ≤0.1% | ≤1% | Controlled synthetic environment |
| Time Sync | ±200 µs PTP hardware | ±1 ms software timestamp | No hardware PTP available |
| Model AUC | ≥0.90 | ≥0.85 | Synthetic data, prototype model |
| False Positive Rate | ≤2% | ≤5% | Acceptable for prototype |
| Position Error | 0.2 m at 1 kHz | Simulated only | No physical radar hardware |

## In Scope (Prototype)

- Full architectural pipeline from ingestion to dashboard

- ALICE Open Data ingestion (small sample subset)

- Synthetic radar / LIDAR / telemetry data generation

- Kafka + Spark Streaming pipeline (Docker Compose)

- Multi-source data fusion with software timestamps

- AI anomaly detection model with explainable outputs (SHAP)

- Real-time dashboard with all key pages

- Performance testing report with prototype bar measurements

- Full technical documentation and final presentation

## Out of Scope (Industrial Version Only)

- TRL 5-7 operational environment validation

- STANAG-certified radar interface integration

- Hardware PTP synchronization

- Production throughput (200K events/sec)

- KMS-based key management infrastructure

- On-prem / edge production deployment

- Patent applications and commercialization

- Federated multi-site deployment (V3)

- Pilot user feedback loop with defense or industrial partner

# 4. Tech Stack

| Layer | Technology | Rationale |
| --- | --- | --- |
| Backend / API | FastAPI (Python) | Async, Python-native, integrates with AI/ML layer |
| Streaming | Apache Kafka (Docker) | Industry standard, official Dataseed choice |
| Stream Processing | PySpark / Structured Streaming | Python-first, official Dataseed choice |
| Database | TimescaleDB (PostgreSQL) | Time-series optimized; SQL knowledge transfers |
| Frontend | ReactJS | Beyza's primary expertise |
| Data Formats | Avro (stream) + Parquet (storage) | Schema evolution support, columnar efficiency |
| AI/ML | scikit-learn, PyTorch (TBD) | Standard for anomaly detection |
| Explainable AI | SHAP | De facto standard for feature attribution |
| Containerization | Docker + Docker Compose | Local laptop deployment |
| Version Control | GitHub | Standard collaboration platform |
| CI/CD | GitHub Actions | Free for public repos, automated testing |

# 5. 10-Milestone Overview

Each milestone runs roughly 4 weeks except Milestone 9 (8 weeks for dashboard/integration) and Milestone 10 (8 weeks for testing/final delivery). Detailed week-by-week task breakdowns are produced as the team enters each milestone — this roadmap stays a living document.

| # | Milestone | Dates | Weeks | Main Output |
| --- | --- | --- | --- | --- |
| M1 | Project Understanding & Requirements | 11 May – 7 Jun 2026 | 1–4 | Scope reconciliation, architecture, GitHub repo, prototype bar locked |
| M2 | Data Schema & Model Design | 8 Jun – 5 Jul 2026 | 5–8 | ALICE / sensor / fused Avro schemas, database ERD, API contracts |
| M3 | Data Generation & Preprocessing | 6 Jul – 2 Aug 2026 | 9–12 | ALICE Run 3 sample acquired, synthetic radar/LIDAR/telemetry datasets |
| M4 | Data Adaptation Layer | 3 Aug – 30 Aug 2026 | 13–16 | Avro/Parquet conversion pipeline, schema registry |
| M5 | Streaming Pipeline | 31 Aug – 27 Sep 2026 | 17–20 | Working Kafka + Spark Streaming pipeline |
| M6 | Data Fusion & Synchronization | 28 Sep – 25 Oct 2026 | 21–24 | Multi-source fusion engine, sync validation |
| M7 | AI/ML Anomaly Detection | 26 Oct – 22 Nov 2026 | 25–28 | Trained model meeting AUC ≥ 0.85 |
| M8 | Explainable AI Layer | 23 Nov – 20 Dec 2026 | 29–32 | SHAP-based explanation module |
| M9 | Dashboard, API & Integration | 21 Dec 2026 – 14 Feb 2027 | 33–40 | Full dashboard, FastAPI backend, end-to-end demo |
| M10 | Testing & Final Delivery | 15 Feb – 9 Apr 2027 | 41–48 | Performance report, final prototype, presentation, demo video |

# 6. Milestone Summaries

## Milestone 1 — Project Understanding & Requirements

Dates: 11 May – 7 June 2026 · Weeks 1–4

Goal: Lock the project scope, requirements, architecture, tech stack, and performance targets in writing. Set up the development environment. Produce a scope reconciliation document for Emrah's sign-off.

Key Deliverables: Scope reconciliation doc, requirements list, architecture diagram, GitHub repo with folder structure, prototype performance bar, risk register v1, Docker Desktop installed on all 3 laptops.

## Milestone 2 — Data Schema & Model Design

Dates: 8 June – 5 July 2026 · Weeks 5–8

Goal: Design the structure of ALICE-like event data, sensor data, and fused records. Define schema evolution policy and the database ERD.

Key Deliverables: ALICE event schema (Avro), sensor schema (Avro), fused schema (Avro), TimescaleDB ERD, API response contracts, data dictionary.

## Milestone 3 — Data Generation & Preprocessing

Dates: 6 July – 2 August 2026 · Weeks 9–12

Goal: Acquire ALICE Run 3 sample data from CERN Open Data Portal. Build synthetic sensor data generators that produce realistic radar, LIDAR, and telemetry streams.

Key Deliverables: ALICE sample dataset, synthetic data generator scripts, labeled training data, data quality validation report.

## Milestone 4 — Data Adaptation Layer

Dates: 3 August – 30 August 2026 · Weeks 13–16

Goal: Build the layer that converts raw inputs into standardized Avro/Parquet formats with proper schema versioning.

Key Deliverables: Adaptation pipeline, schema registry setup, format conversion tests.

## Milestone 5 — Streaming Pipeline

Dates: 31 August – 27 September 2026 · Weeks 17–20

Goal: Stand up Apache Kafka in Docker Compose and build the Spark Structured Streaming jobs that consume, process, and route events.

Key Deliverables: Working streaming pipeline, throughput benchmarks against prototype bar, watermark/window logic.

## Milestone 6 — Data Fusion & Synchronization

Dates: 28 September – 25 October 2026 · Weeks 21–24

Goal: Merge ALICE-like and sensor streams using software timestamps. Handle late and out-of-order events.

Key Deliverables: Fusion engine, synchronization validation, fused output stream.

## Milestone 7 — AI/ML Anomaly Detection

Dates: 26 October – 22 November 2026 · Weeks 25–28

Goal: Train and validate anomaly detection model on fused data. Hit prototype bar of AUC ≥ 0.85 and FPR ≤ 5%.

Key Deliverables: Trained model, evaluation report, baseline comparison.

## Milestone 8 — Explainable AI Layer

Dates: 23 November – 20 December 2026 · Weeks 29–32

Goal: Integrate SHAP for feature attribution. Build the explanation pipeline that outputs human-readable reasoning for every alert.

Key Deliverables: XAI module, explanation outputs in fused schema, cause-effect chain logic.

## Milestone 9 — Dashboard, API & Integration

Dates: 21 December 2026 – 14 February 2027 · Weeks 33–40 (8 weeks)

Goal: Build full ReactJS dashboard with 7 pages (Home, Live Stream, Fusion Monitor, AI Alerts, XAI Panel, Performance, Reports). Connect FastAPI backend. Run first end-to-end demo.

Key Deliverables: Dashboard frontend, FastAPI backend, TimescaleDB integrated, full pipeline live, demo scenario recorded.

## Milestone 10 — Testing & Final Delivery

Dates: 15 February – 9 April 2027 · Weeks 41–48 (8 weeks)

Goal: Run full performance test suite against prototype bar. Fix bugs. Prepare final technical report and presentation for Emrah and Dataseed team.

Key Deliverables: Performance test report, final prototype, technical report, presentation, demo video, GitHub README.

# 7. Risk Register (Initial)

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| 12-month timeline tight for full pipeline + AI + dashboard | Medium | High | Aggressive scope reconciliation; cut features rather than extend deadline; review at end of each milestone |
| CERN ALICE Run 3 data format more complex than expected | Medium | Medium | Early data exploration in M3; consult Prof. Ayben fall back to smaller dataset if needed |
| Performance targets unreachable on laptop hardware | Medium | Medium | Prototype bar agreed in M1 with Emrah; document the gap honestly in M10 report |
| Tech stack learning curves slow Week 1-8 progress | Medium | Medium | Pair learning; weekly sync on blockers; reduce M2-M3 scope if needed |

# 8. Communication & Reporting Cadence

| Meeting / Report | Frequency | Day / Time | Purpose |
| --- | --- | --- | --- |
| Team planning meeting | Weekly | Tuesday | Plan the week's tasks, surface blockers |
| Progress review | Weekly | Saturday | Review what shipped, what slipped, what's at risk |
| Emrah weekly update | Weekly | Friday | 1-page written report — progress, blockers, next week's plan |
| Milestone review with Emrah | Monthly | End of each milestone | Demo deliverables, get sign-off, raise risks |
| Prof. Ayben consultation |  | As needed | ALICE data, scientific methodology, validation questions |

# 9. Final Deliverables Checklist

By 9 April 2027, the following must be ready to present to Emrah and the Dataseed team:

| Deliverable | Owner | Format |
| --- | --- | --- |
| Working prototype (runnable via docker-compose up) | All | GitHub repo |
| Source code with README | Abdalla | GitHub |
| ALICE data ingestion module | Omer | Python |
| Synthetic sensor data generation | Omer | Python |
| Streaming pipeline (Kafka + Spark) | Omer | Docker Compose |
| Data fusion module | Omer + Abdalla | PySpark |
| AI anomaly detection model | Abdalla | Python (.pkl / .pt) |
| XAI explanation module | Abdalla | Python (SHAP) |
| Dashboard (7 pages) | Beyza | ReactJS |
| FastAPI backend | Beyza | Python |
| TimescaleDB schema + data | Beyza | SQL + Docker |
| Performance testing report | Omer + Abdalla | PDF |
| Technical documentation | Abdalla | Markdown / PDF |
| Final presentation slides | Abdalla + Beyza | PPTX / PDF |
| Demo video | All | MP4 (recommended) |

This roadmap is a living document. Each milestone's detailed week-by-week breakdown will be produced as the team approaches it.