DataForge Risk Register — v1

Purpose: This register identifies and mitigates risks to the DataForge 12-month prototype delivery. It is a living document — reviewed and updated at every milestone review. Risks are assessed on two dimensions: Likelihood (probability of occurring) and Impact (consequence if it occurs). Risk Level is derived from the combination. v1 covers 9 risks: 7 required (R-01–R-07) + 2 additional risks identified by the project lead (R-08: M9 integration mismatches; R-09: synthetic data representativeness).

Risk Level Legend

| Level | Meaning | Level | Meaning |
| --- | --- | --- | --- |
| Critical | H × H — Immediate action required; escalate to Emrah | High | H × M or M × H — Active mitigation plan required |
| Medium | M × M or L × H — Monitor weekly; mitigation in place | Low | L × M or L × L — Monitor at milestone reviews |

Risk Register

| ID | Risk Description | Likelihood | Impact | Level | Mitigation Actions | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| R-01 | Docker Installation Failure Docker Desktop may fail to install or run on team laptops, particularly on Windows Home (lacks Hyper-V) or older hardware with insufficient RAM. | Medium | Medium | Medium | - Test Docker installation on all 3 laptops in Week 1 before any pipeline work begins. - Prepare a WSL2 setup guide for Windows Home users as standard fallback. - If WSL2 fails, provision a lightweight Ubuntu VM (VirtualBox) as a last resort. - Budget half a day per laptop for troubleshooting; flag blockers to Emrah if unresolved by Day 3. | Omer + Abdullah |
| R-02 | CERN Data Format Complexity ALICE Run 3 data is distributed as ROOT (.root) binary files. Parsing ROOT format in Python requires the uproot library, which may have version incompatibilities or missing field mappings not apparent until M3. | Medium | Medium | Medium | - Omer completes CERN Open Data Portal exploration in Week 2 and documents exact field names and file sizes. - Use uproot library (tested with ALICE ROOT files) — install and verify in M3 Week 9. - Consult Prof. Dr. Ayben Karasu Uysal via Emrah if field semantics are unclear. - Fallback: use a smaller ALICE Run 2 sample dataset (simpler format) if Run 3 proves intractable. | Omer + Abdullah |
| R-03 | Performance Targets Unreachable on Laptop Hardware The Prototype Bar targets (≥10K events/sec, ≤500 ms p95 latency) are calibrated for laptop Docker Compose, but specific laptops with less than 16 GB RAM or slow storage may fall short. | Low | High | Medium | - Prototype Bar was set conservatively in M1 with Emrah's agreement — targets already account for laptop overhead. - Run throughput benchmarks early in M5 (not just M10) to surface shortfalls before the final milestone. - If targets are missed, document the gap transparently in the M10 performance report with hardware context. - As a last resort, reduce synthetic generator rate to 5K events/sec and document the revised baseline. | Abdullah |
| R-04 | Tech Stack Learning Curves Slowing Progress Kafka, PySpark Structured Streaming, and TimescaleDB are new to all or most team members. Steep learning curves in M1–M3 could delay M5 streaming implementation and create a cascade of late milestones. | High | Medium | High | - M1 Weeks 1–2 are structured as dedicated learning sprints — no implementation pressure before M4. - Omer completes Kafka 101 + PySpark intro tutorials with documented learning notes before M5. - Beyza begins TimescaleDB tutorials in Week 1; Abdullah pairs with Beyza if blockers emerge by Friday. - Weekly Tuesday meetings surface learning blockers early; any unresolved blocker > 2 days triggers a sync with Abdullah. - Reduce M2–M3 scope if learning curves exceed estimates — cut features rather than extend deadline. | All — Abdullah (coordination) |
| R-05 | Emrah Scope Review Feedback Requiring Rework Emrah may review the Scope Reconciliation Document or Requirements Document and request significant changes — adding features, adjusting performance targets, or re-aligning with the industrial proposal — causing rework across M1 deliverables. | Medium | High | High | - Establish weekly Friday updates to Emrah from Day 1 to surface misalignments early, not at milestone reviews. - Submit Scope Reconciliation Document and Prototype Performance Bar by Wednesday 28 May — giving time to iterate before Friday. - Frame all deliverables against the explicitly agreed scope to limit surface area for new requirements. - If rework is requested, log it formally as a scope change with impact on timeline and escalate to the M1 review call. | Abdullah |
| R-06 | AI Model Not Reaching AUC ≥ 0.85 on Synthetic Data The Isolation Forest model is the required baseline. Synthetic anomaly labels may be too simple or the feature space too sparse, resulting in AUC below the 0.85 Prototype Bar threshold. | Medium | High | High | - Design synthetic anomaly generators in M3 to produce realistic, multi-class anomaly distributions (not just random noise). - Reserve a stratified 20% test set from the start to ensure AUC is measured on genuinely held-out data. - Tune Isolation Forest hyperparameters (n_estimators, contamination fraction) systematically before concluding model is insufficient. - If AUC < 0.85 after tuning: augment training set with additional synthetic anomaly types or adjust the contamination prior. - PyTorch deep model is available as a stretch goal fallback — does not block M7 sign-off if Isolation Forest succeeds. | Abdullah |
| R-07 | Team Bandwidth During Exam and Holiday Periods As a student team, exam periods (typically January and June) and public holidays may reduce working capacity by 50–100% for 2–3 week stretches, creating gaps in milestone delivery. | High | Medium | High | - Map exam periods and public holidays onto the milestone timeline in Week 1; identify at-risk weeks explicitly. - Front-load deliverables in the weeks before known crunch periods — do not leave documentation to the last week. - Define minimum-viable output for each milestone so partial delivery is still reviewable by Emrah. - Notify Emrah in advance if a milestone delivery will be delayed due to exam period — never surprise with a late submission. | Abdullah (scheduling) + All |
| R-08 | M9 Integration Reveals Architectural Mismatches The first full end-to-end integration of all 10 modules happens in M9. Discovering that Module 5 output schema does not match Module 6 input, or that API contracts mismatch dashboard requirements, at that late stage could require 2–4 weeks of backtracking. | Medium | High | High | - Lock all inter-module interface contracts (Avro schemas, Kafka topic names, API response shapes) in M1–M2 and commit to /docs/. - Test module-to-module integration incrementally: M5 tests Modules 3→4, M6 tests Modules 4→5→6, M7 tests Modules 6→7. - Run a lightweight end-to-end smoke test (stub modules) in M5 to verify pipeline connectivity before any AI/ML work. - Abdullah reviews each module's interface contract before Omer or Beyza begins implementation. | Abdullah |
| R-09 | Synthetic Data Not Representative for Meaningful Validation If the synthetic radar/LIDAR/telemetry generators produce data that is too uniform or too random, the AI model and fusion logic may pass tests only because the test data mirrors the training data — not because the system actually works. | Medium | Medium | Medium | - Design generators in M3 to produce realistic temporal patterns: burst anomalies, sensor dropout, correlated multi-sensor events. - Validate generator output statistics against publicly available ALICE Run 3 data distributions as a sanity check. - Consult Prof. Dr. Ayben Karasu Uysal on realistic anomaly rates and event signatures before generator finalisation. - Include a data quality validation report in the M3 deliverables — reviewed by Abdullah before AI training begins. | Abdullah + Omer |

| Risk Summary | Critical | High | Medium | Low |
| --- | --- | --- | --- | --- |
| 9 risks identified (v1) | 0 | 5 | 4 | 0 — no Low risks at project start |